## Sheet1
guideline for the risk description:
Event may occur, causing Impact.			Description of Risk	Probability (1-10)	Impact (1-10)	Priority	Triggers	Response Plan
If Cause exists, Event may occur, leading to Effect.	Technical:	Gripper	servo breaks without prompting	2	5	10
			gripper self-destructs breaking servo	3	5	15
A good risk register has the following six columns:			gripper self-destructs breaking plastics	3	2	6
		kinect:				0
Description of risk			Power supply voltage issues	2	7	14
Probability			Runs too slowly on second PC	4	3	12
Impact			Issues translating kinect pixel numbers to coordinate referenced to any robot	3	8	24
Priority		Gripper vision:				0
Triggers			fractal QR codes don't work	5	8	40
Response plan			camera too close, fractal QR code doesn't work	6	8	48
			gripper/kinect vision uses up too many computational resources causing issues with kinematic calculations resulting in:
			Non-smooth trajectories	5	2	10
			Jumping	4	3	12
			collisions with other objects	3	6	18
			Collisions with self	3	6	18
			gripper can't deform to shape of object properly, can't pick object up	3	6	18
Response strategies:		localisation:
Acceptance: Also known as retention, the project manager or organization is willing live with the risk without further mitigation.			Robot crashes into walls/things resulting in:	6		0
Avoidance: The project can avoid the risk by removing whatever requirement caused it to appear. The risk is sidestepped.			breaks nothing	8	1	8
Control: Also called mitigation, this involves recognizing the risk is there and performing actions to minimize it, developing contingency plans in case the risk comes to pass, or developing fall-back provisions.			breaks arm	3	6	18
Transfer: Sharing of the risk with another party, or outright transfer (wouldn’t that be nice!)			breaks encoder	3	6	18
			robot can't get close enough to object (more than once or twice)	3	7	21
		object mapping:				0
			Robot can't see far away objects (1.5m+)	3	7	21
			robot falsly identifies objects	2	7	14
					0
		arm mounting:				0
			arm falls off leading to damage of arm	3	7	21
			arm overbalances base	2	9	18
		systems integration:				0
			must and can't stop/pause SLAM without remapping room	4	9	36
		object falls out of gripper often		3	7	21
			risk: invacare remote finally dies	3	7	21		reserve budget to buy new controller
					0
	Planning:		Fiinished subsystems performance criteria not strict enough to allow for autonomous interaction between subsystems	3	7	21	Unacceptable performance of interaction between systems	silution: carefully re-evaluate performance criteria of subsystems, potentially suggest alternative subsystems
	Human:					0
			lab is frequently full of people during testing/development, scrambles SLAM	4	8	32	More than two days spent at low productivity due to people walking nearby
			Getting caught in the details of a subsystem, spending too long trying to fix unexpected issues in a subsystem	7	7	49	Subsystem developent time exceeded	mitigation: group meeting, analyse alternative subsystems/different ways of achieving the same thing
			risk: Tom/Dan falls ill for:			0
			1 week	2	7	14
			2-4 weeks	2	8	16
			4-8 weeks	1	9	9
			8 weeks +	1	10	10
			CAD could take longer than planned	3	3	9	CAD development time exceeded	Remaining workload redistributed between us
	human/time:		Systems integration takes longer than planned (applicable for interaction between every system&subsystem)	7	7	49	Systems integration time exceeded (or looks like it will be)	Reduce scope of project, re-evaluate priority list, divert attention from lower priority tasks, look for potential off-the shelf solutions (unlikely to find any)
			Risk: we lose access to the arm from Martin	1	10	10
	Resources:		Printers unavailable / break	2	2	4
	Logistics:		long lead times	8	4	32
			can't return servos if faulty / break	6	6	36		Order more servos if our surplus falls below two
			can't get PCB made	1	8	8		Point to point wiring
	Other:		We lose the laptop	2	9	18
			We lose the arm	2	9	18