## Sheet1
		Description of Risk	Probability (1-10)	Impact (1-10)	Priority (probability * impact)	Triggers (if not obvious)	Response Plan
Technical:	Gripper	servo breaks without prompting	2	5	10		If servo is from china replace with one of the spares and order another. If servo is from UK, replace with spare and begin RMA process
		gripper self-destructs breaking servo	3	5	15		Replace servo with spare and order another spare
		gripper self-destructs breaking plastics	3	2	6		Re-print (one day lost)
	kinect:
		Power supply voltage issues	2	7	14	Power supply moves more than 0.5v out of specification	Monitor closely for the first few days
		Runs too slowly on second PC	4	3	12	Major issues occur	Optimise hectorSLAM
		Issues translating kinect pixel numbers to coordinate referenced to any robot frame	3	8	24		Seek advice on TF from lecturers, if that doesn't work then group meeting (and both work on solution)
	Gripper vision:
		fractal QR codes don't work	5	8	40		Solution explained in main execution plan
		camera too close, fractal QR code doesn't work	6	8	48		" " " " " " " " " " " " "
		gripper/kinect vision uses up too many computational resources causing issues with kinematic calculations resulting in:					Optimise hectorSLAM to reduce computational requirements
		Non-smooth trajectories	5	2	10		Minor issue
		Jumping	4	3	12		Medium issue, investivate
		collisions with other objects	3	6	18		Major issue, re-evaulate computational requirements
		Collisions with self	3	6	18		" " " " " " " " " " " "
		gripper can't deform to shape of object properly, can't pick object up	3	6	18	Object frequently drops from gripper	Attach 'bag' to gripper, if tht fails discuss redesign
	localisation:
		Robot crashes into walls/things resulting in:
		breaks nothing	8	1	8		Be more careful
		breaks arm plastics	3	6	18		Re-print (two days lost)
		breaks arm servo	3	9			Major issue, redesign testing approach, look for replacement whilst initiating RMA to korea
		breaks encoder	3	6	18		Fix encoder (two days lost)
		robot can't get close enough to object (more than once or twice)	3	7	21		Tune navigation systems, if fails then team meeting
	object mapping:
		Robot can't see far away objects (1.5m+)	3	7	21		Should be addressed in development phase 1
		robot falsly identifies objects	2	7	14		Both team members quickly construct a filter where a number of successful matches have to happen in sequence in order to trigger 'object found'
					0
	arm mounting:
		arm falls off leading to damage of arm	3	7	21		Major issue, reevaluate testing
		arm overbalances base	2	9	18		Major issue, should never happen. Back of envelope calculations should be done to analyse potential moments between arm and base
	systems integration:
		must and can't stop/pause SLAM without remapping room	4	9	36		Group meeting, consider archetecture re-design
	object falls out of gripper often		3	7	21
		risk: invacare remote finally dies	3	7	21		reserve budget to buy new controller
Planning:		Fiinished subsystems performance criteria not strict enough to allow for autonomous interaction between subsystems	3	7	21	Unacceptable performance of interaction between systems	Carefully re-evaluate performance criteria of subsystems, potentially suggest alternative subsystems
Human:
		lab is frequently full of people during testing/development, scrambles SLAM	4	8	32	More than two days spent at low productivity due to people walking nearby
		Getting caught in the details of a subsystem, spending too long trying to fix unexpected issues in a subsystem	7	7	49	Subsystem developent time exceeded	Group meeting, analyse alternative subsystems/different ways of achieving the same thing
		risk: Tom/Dan falls ill for:
		1 week	2	7	14		Must catch up with lost work, consider extenuating circumstances
		2-4 weeks	2	8	16		Significant issue, discuss catching up, probably reduce project scope, consider extenuating circumstances
		4-8 weeks	1	9	9		Major issue, reduce scope and file for extenuating circumstances
		8 weeks +	1	10	10		Major issue, drastically reduce scope and file for extenuating circumstances
		CAD could take longer than planned	3	3	9	CAD development time exceeded	Remaining workload redistributed between us
human/time:		Systems integration takes longer than planned (applicable for interaction between every system&subsystem)	7	7	49	Systems integration time exceeded (or looks like it will be)	Reduce scope of project, re-evaluate priority list, divert attention from lower priority tasks, look for potential off-the shelf solutions (unlikely to find any)
		Risk: we lose access to the arm from Martin	1	10	10		Unlikey and catastrophic, total re-design of project goals
Resources:		Printers unavailable / break	2	2	4		Unlikely, we have two personal printers and at least three available in University
Logistics:		long lead times	8	4	32		Plan accordingly, all long-lead items to be specified within the first week of February
		can't return servos if faulty / break	6	6	36		Order more servos if our surplus falls below two
		can't get PCB made	1	8	8		Point to point wiring
Other:		We lose the laptop	2	9	18		Insure laptop, major issue