## Sheet1
		Description of Risk	Probability (1-10)	Impact (1-10)	Priority	Triggers	Response Plan
Technical:	Gripper	servo breaks without prompting	2	5	10
		gripper self-destructs breaking servo	3	5	15
		gripper self-destructs breaking plastics	3	2	6
	kinect:				0
		Power supply voltage issues	2	7	14
		Runs too slowly on second PC	4	3	12
		Issues translating kinect pixel numbers to coordinate referenced to any robot	3	8	24
	Gripper vision:				0
		fractal QR codes don't work	5	8	40
		camera too close, fractal QR code doesn't work	6	8	48
		gripper/kinect vision uses up too many computational resources causing issues with kinematic calculations resulting in:
		Non-smooth trajectories	5	2	10
		Jumping	4	3	12
		collisions with other objects	3	6	18
		Collisions with self	3	6	18
		gripper can't deform to shape of object properly, can't pick object up	3	6	18
	localisation:
		Robot crashes into walls/things resulting in:	6		0
		breaks nothing	8	1	8
		breaks arm	3	6	18
		breaks encoder	3	6	18
		robot can't get close enough to object (more than once or twice)	3	7	21
	object mapping:				0
		Robot can't see far away objects (1.5m+)	3	7	21
		robot falsly identifies objects	2	7	14
					0
	arm mounting:				0
		arm falls off leading to damage of arm	3	7	21
		arm overbalances base	2	9	18
	systems integration:				0
		must and can't stop/pause SLAM without remapping room	4	9	36
	object falls out of gripper often		3	7	21
		risk: invacare remote finally dies	3	7	21		reserve budget to buy new controller
					0
Planning:		Fiinished subsystems performance criteria not strict enough to allow for autonomous interaction between subsystems	3	7	21	Unacceptable performance of interaction between systems	Carefully re-evaluate performance criteria of subsystems, potentially suggest alternative subsystems
Human:					0
		lab is frequently full of people during testing/development, scrambles SLAM	4	8	32	More than two days spent at low productivity due to people walking nearby
		Getting caught in the details of a subsystem, spending too long trying to fix unexpected issues in a subsystem	7	7	49	Subsystem developent time exceeded	Group meeting, analyse alternative subsystems/different ways of achieving the same thing
		risk: Tom/Dan falls ill for:			0
		1 week	2	7	14
		2-4 weeks	2	8	16
		4-8 weeks	1	9	9
		8 weeks +	1	10	10
		CAD could take longer than planned	3	3	9	CAD development time exceeded	Remaining workload redistributed between us
human/time:		Systems integration takes longer than planned (applicable for interaction between every system&subsystem)	7	7	49	Systems integration time exceeded (or looks like it will be)	Reduce scope of project, re-evaluate priority list, divert attention from lower priority tasks, look for potential off-the shelf solutions (unlikely to find any)
		Risk: we lose access to the arm from Martin	1	10	10
Resources:		Printers unavailable / break	2	2	4
Logistics:		long lead times	8	4	32
		can't return servos if faulty / break	6	6	36		Order more servos if our surplus falls below two
		can't get PCB made	1	8	8		Point to point wiring
Other:		We lose the laptop	2	9	18
		We lose the arm	2	9	18